## Slide 1: STEWARDING OUTCOMES OF EARLY ACTION FOR IMPACT PROJECT
Grant size: £ 25,000
Duration: April 2025 - March 2026

## Slide 2: Background
The major problem is limited understanding of anticipatory action at both district and community level as this is new approach to Gwanda with EAFI being the first of its kind. The phase 1 project was implemented in an emergence mode and within a short period of time which encumbered entrenching robust sustainability mechanisms and tapping on valuable lessons learnt that ensued post implementation. This anticipatory action intervention thus seeks to reinforce systems and secure investments from the first phase of the project. A key factor in reinforcing systems will be forging robust linkages between communities, suppliers and markets. Further the intervention will seek to inculcate anticipatory action through capacity building and awareness creation. The lack of anticipatory action makes the lives of people living in poverty susceptible to shocks and disasters which results in loss of lives and assets as well as high costs for mitigation and recovery. For instance, the Chronicle of 16 October 2024 reported that the district was losing 900 cattle a week which was a big loss to farmers owing to lack of anticipatory actions by both farmers and the duty bearer.
Lack of anticipatory action adversely impacts on the lives of people living in poverty in several ways, with groups affected differently according to their categories as follows:
Women and Girls: Women and girls have increased workload and responsibility for caring for family members affected by disasters, potential loss of income-generating activities, and heightened risk of gender-based violence.

## Slide 3: Background
People with Disabilities: Limited access to resources, services, and support during disasters, exacerbating existing challenges and vulnerabilities.
Men and Youth: Loss of livelihoods, increased poverty, and potential migration in search of better opportunities, disrupting family structures and social cohesion.
Anticipatory action proffers solutions that enable people to improved resilience to climate-related disasters, enhance food security and nutrition as well as increase access to resources, services and support for vulnerable groups. Further anticipatory action will empower communities to better maintain and utilize infrastructure, such as water schemes and irrigation systems strengthening community ownership and capacity for sustainable development.

## Slide 4: Project overview
Target Beneficiaries: 11,374 vulnerable households (~13,974 persons), including 2% with disabilities.
Geographical Focus: Gwanda District, Matabeleland South, Zimbabwe (Wards 11, 16, 19, 20).

## Slide 5: Targeted Groups and Impact
Men, Women, Girls, Boys: Benefit from improved water and disaster preparedness.
People with Disabilities: Increased inclusion and access to resources.
Community Ownership: Empowerment through participation and insurance schemes.

## Slide 6: Objectives
To secure the gains achieved by the phase 1 project through reinforcing sustainability systems and mechanisms for project wards in Gwanda South by March 2026.
To strengthen public private partnerships between farmers, seed houses and suppliers of equipment and farming input including knowledge for targeted wards.

## Slide 7: Activities: Objective 1
Objective 1 | Activities | Outputs
To entrench a robust sustainability plan for water systems and enhance community ownership and capacity, ensuring the long-term positive outcomes of the Early Action for Impact project in Gwanda South by March 2026 | Conduct 1 District inception meeting for 30 people (17male and 13 female). | 1 district inception meeting conducted
 | Conduct 4 ward inception meetings for 400 participants (240 female and 160 male). | 1 district inception meeting conducted. 4 ward inception meetings conducted.
 | Conduct workshop to review and strengthen the District DRR plan (30 participants -17 male and 13 female) | District DRR plan reviewed, and gaps identified 1 reviewed DDR plan document produced

## Slide 8: Cont’
Objective 1 | Activities | Outputs
To entrench a robust sustainability plan for water systems and enhance community ownership and capacity, ensuring the long-term positive outcomes of the Early Action for Impact project in Gwanda South by March 2026 | Cascade the revised DRR plans to communities in the four wards targeting 400 participants (240female and 160 male). | Revised DRR plans cascaded to four wards
 | Facilitate radio programs on anticipatory action plans and early warning reaching a listenership of 60000 (36000 female and 24000 male). | 6 monthly radio broadcasts conducted during.
 | Develop and entrench a robust COMPASS system to enable real time information sharing (30 participants,18female and 12male) | COMPASS system established for the project

## Slide 9: Cont’
Objective 1 | Activities | Outputs
To entrench a robust sustainability plan for water systems and enhance community ownership and capacity, ensuring the long-term positive outcomes of the Early Action for Impact project in Gwanda South by March 2026 | Conduct district level performance review workshop of the water systems and livelihoods interventions to establish utility, gaps and opportunities for extending impact. (30 participants,17 female and 13male) | One district level meeting conducted
 | Conduct performance review of the water systems to establish utility, gaps and opportunities for extending impact. (325 participants,200 female and 125male) | One report generated
 | Strengthen existing water point by-laws incorporating insurance mechanisms (325 participants,200 female and 125 male) | 5 water point by-laws strengthened

## Slide 10: Cont’
Objective 1 | Activities | Outputs
To entrench a robust sustainability plan for water systems and enhance community ownership and capacity, ensuring the long-term positive outcomes of the Early Action for Impact project in Gwanda South by March 2026 | Build the capacity of women to maintain and manage water infrastructure (150 participants,100 female and 50 male). | 5 trainings conducted
 | Conduct performance review of livelihood interventions to establish utility, gaps and opportunities for extending impact. (120 participants,80female and 40male). | One report generated
 | Strengthen existing water point by-laws incorporating insurance mechanisms (325 participants,200 female and 125 male) | 5 water point by-laws strengthened

## Slide 11: Activities: Objective 2
Objective 2 | Activities | Outputs
To strengthen public private partnerships between farmers, seed houses and suppliers of equipment and farming input including knowledge for targeted wards. | Mobilise, and motivate stakeholders, suppliers, buyers and the communities to participate in knowledge fairs (500 participants) | 9 mobilisation meetings conducted.
 | Strengthen the farmers platforms for information sharing (1000 participants,600 female and 400female). | 4platforms strengthened
 | Organise three knowledge fairs to link farmers with private sector actors (suppliers and buyers) targeting 1000 participants,600 female and 400male) | 3 knowledge fairs conducted for four wards

## Slide 12: Cont’
Objective 2 | Activities | Outputs
To strengthen public private partnerships between farmers, seed houses and suppliers of equipment and farming input including knowledge for targeted wards. | Documentation and dissemination of lessons learnt and impact stories. | One lesson learnt document produced
 | Conduct closeout meeting at district level for 30 people (17male and 13 female). | 1 closeout meeting conducted at district level

## Slide 13: Expected Results
Adoption of water system insurance policies.
1
Improved collaboration between farmers and private sector.
2
Enhanced community resilience and sustainability of water infrastructure.
3